## Sheet1
|  | GAME TITLE | TEAM NAME
Week | Day | Tech Milestone | Art Milestone | ART ASSET DESCRIPTIONS
2 | Mon, Mar 22
| Tue, Mar 23 | Source control site created |  | Textures:
| Thu, Mar 25 |  | Game textures delivered to tech | Environment:
| Fri, Mar 26 |  |  | Static Model:
3 | Mon, Mar 29 |  |  | Main Character:
| Tue, Mar 30 |  | Base environment delived to tech | Character Animations:
| Thu, Apr 1 | Base environment integrated | Rough static model for critique | Interactive Sounds:
| Fri, Apr 2 | Game Web Site Online |  | Environmental Sounds:
4 | Mon, Apr 5 | Basic game mechanic implemented |  | Other:
| Tue, Apr 6 |  | Static models delivered to tech
| Thu, Apr 8 | Static models integrated | Rough hi-rez main character for critique
| Fri, Apr 9 |  |  |  | ...
5 | Mon, Apr 12 | Progress Presentation |  | TECH COMPONENT DESCRIPTIONS
| Tue, Apr 13 |  | Main character delivered to tech
| Thu, Apr 15 | Main character integrated | Rough character animations for critique | Controller:
| Fri, Apr 16 |  |  | GUI:
6 | Tue, Apr 20 | First Playable Demo |  | Physics:
|  |  | 4 character animations delivered to tech | AI:
| Fri, Apr 23 | Character animations integrated |  | Networking:
7 | Mon, Apr 26 | Feature Freeze Demo |  | Other:
4 interactive sounds delivered to tech
Tue, Apr 27
| Thu, Apr 29 | Interactive sounds integrated | 4 environmental sounds delivered to tech
| Fri, Apr 30 | Environmental sournds integrated
8 | Mon, May 3 | Final Presentation
| Tue, May 4 |  | Final art portfolio due