## Slide 1: Iterative Development
Notes: Much from Robert Lindeman, IMGD 3000, C-term 2011

## Slide 2: Motivation
Last thing you want to do is write critical code near end of a project
  Induces huge stress on team
  Introduces all kinds of “interesting” bugs that break working code
Testing always gets cut in crunch
  Makes problem even worse!
Planning can help avoid writing critical code in alpha or beta phases

## Slide 3: Wishes versus Reality
Most games you make are smaller/less than you originally envisioned
  Design was bigger than implementation
  Or, tested/working implementation bigger than what made it into game
That’s ok  expect it
So, how do we know when a game is “done”?

## Slide 4: How Do We Estimate Progress?
Example:
Jo is a programmer
She estimates it will take 10 days to implement Smart Trap
She is 4 days into implementation
Is Smart Trap 40% complete? … maybe
  We may not see it "snap shut" until day 9
She’s good,  finishes in 8 days total
  Yay, we are ahead!
Later, decide to add functionality to Smart Trap (e.g., trap large bad guys, too)
  Takes 4 days
Boo, now we’re behind!

## Slide 5: What’s the Point?
Most things get revisited multiple times during development
  Fix bugs, modify functionality, etc.
  “Refactoring” your code
    Note, refactoring easier with clear, easy-to-understand code!
  Expect this! Despite your careful planning …
So, the "40% done" estimate looks pretty sketchy…
Need way to account for time without driving project into trouble (and into panic)

## Slide 6: Incremental Delivery
Milestones are good things!
  They let us get things “done”
Milestones can have downside
  If you miss one, people notice, action taken
  Especially management people
Developer’s view
  Milestones (or plans, in general) are just best guesses for how implementation will evolve
Management’s view
  Schedules are contracts with developers
  Promising certain things at certain times
Different views cause problems
  Developers: panic, pressure, long hours
  Managers: justification for financial pressure

## Slide 7: Milestones (1 of 2)
Despite problems, necessary
  Without milestones, unlikely to get done
Unrealistic milestones mean work not done on time, no matter financial importance
  Remember, are best guesses
Managers need to know estimates of developers and key makers along the way
  Plan financial/time links accordingly
External milestones coarser
  Tie to publishers, marketers, etc.
Internal milestones have finer granularity
  Used by team members

## Slide 8: Milestones (2 of 2)
Think of development plan as black box
  Managers have specific “interface” to box
    “Give me the latest build”
    “Give me the latest (high-level) schedule”
Clearly, this is too simplistic/wishful thinking
  Managers just want to know more (and need to, to do their jobs better)
But view as development plan as “black box” helps separate job roles better

## Slide 9: There is More than Meets the Eye
For many, “if I can’t see it, it is not important”
  AI takes time to build (and you don’t see it)
  Network code to balance players is an optimization (and you don’t see it)
Developers receive less “credit” for unseen code than for things that can be seen
Good managers will probe deeper to see what is really going on
  Requires technical ability (knowledge)
  This is one reason Game Designer needs technical knowledge!

## Slide 10: Iteration
Make frequent working builds
  “We don’t go home Friday until a working build checked in.”
  Frequency (daily or weekly) depends upon project
If management asks for latest build, give one from last week
  Resist desire to show latest-and-greatest
    Won’t always be bug free, ready to show
  People will always expect it and leads to unrealistic expectations

## Slide 11: Internal Scheduling
Give detailed design document
  Make list of all objects (e.g. players, items, NPCs…) that need to be built
  Mark each as one of:
    Core – base, fundamental functionality
    Required – needed for working, playable game
    Desired – icing on the cake, make game special but not required
End result:
  List of features sorted by importance
Note, doing this planning gets easier the more you do!

## Slide 12: Internal Scheduling Structure
Could start from top of milestone list  Work down and when time runs out, then done
  Produces whole lot of “complete” pieces, but no whole that works together
  Makes management (and others) nervous since cannot see it “coming together”
Better way  since list made in Object-Oriented (OO) fashion, start building objects!

## Slide 13: OO Iterative Development – Object Versions (1 of 2)
Create a Stub version of each object
  Complete, but empty
  Perhaps just print out message
Basic version
  Placeholder with some properties present
  Set attributes, minimal functionality
Nominal version
  Commercial viable implementation
  Most functionality in place
  Tested
Optimal version
  State of the art
  All polish present
  Thoroughly tested
// Player.h
class Player {
public:
Player();
~Player();
};
// Player.cpp
#include "Player.h"
Player::Player(){ }
Player::~Player(){ }
Stub
Nice feature about above development plan? Game will “build” even after Basic version!

## Slide 14: OO Iterative Development – Object Versions (2 of 2)
Some objects (classes) will be simpler
  Fewer iterations (e.g. Position class)
Some will be more complex
  More iterations (e.g. WorldManager class)
Can say have shippable game when every object at least in Nominal version
  Working definition of “Good Enough”
A complete game is one where all objects are at Optimal level

## Slide 15: OO Iterative Development – Overall
But, seems like need to write 3 versions of every object!
  Yes, but would probably do that anyway with revisions
Approach
  Starting with core, then required, then desired, implement Stub versions of all objects
  Starting with core, then required, implement Nominal versions
  Code is now releasable
Only now start to work on desired
This is breadth-first approach
  Better than "let's do the cool bits first!"
  Always have build-able game
  Near-continuous growth
  Can easily show refinement
  Throughout, better handle on how "complete" game is

## Slide 16: Scheduling - Naive

## Slide 17: Scheduling – Better (single programmer)
Note! This is just one example  Alternate could be to finish Core Nominal before Base Required
Point is to “zig-zag” to bottom corner, with optimal last

## Slide 18: Scheduling – Better (multiple programmers)

## Slide 19: Team Work
Make sure to use skills of each team member well
Keep everyone busy
  No waiting, if possible
Communication vital!
  Every programmer should be aware of what others are doing
  Code reviews (for sharing implementation details as much as writing solid code)
  Joint status meetings (Daily! Even if brief)
  Documentation (documented code, documented milestones and status, documented bug list)

## Slide 20: Scheduling with Iteration
Shift:
  FROM: When will it be finished?
  TO: When will it be good enough?
"Finished" is meaningless, anyway
Have definition of “good enough" now!
Bad estimation often comes from top-down dissection
  No accounting for learning curve, code revision, or integration
Iterative development
  Total time equals sum of the Stub, Base, Nominal, and Optimal levels

## Slide 21: Consider Saucer Shoot
Core
  Ability for player to move ship, fire bullets
  Saucers move
Required
  Bullets destroy saucers
  Saucers respawn
  Explosions
  Animated Sprites
  Game difficulty progresses and game ends
Desired
  Stars
  Game start screen, game end screen
  Score
____
/__o_\
\
~==-
/

## Slide 22: Consider Dragonfly
(Note, your development did separate 2a, 2b, 2c “mini-projects”)
Core
  Log file management
  Game loop with timing
  Game objects with updates
Required
  User-input
  User-defined events
  Graphics support
  Collisions
Desired
  Animated Sprites
  Efficient scene management (e.g. for collision detection)
  Multi-colored Sprites
  Camera control
Is “optimal” done for any classes?
Probably not – would need all Desired done first!
But have Nominal version of classes for all

## Slide 23: Group Exercise
Split into Project 3 Teams
Make list for your game, with one feature in each list
  Core
  Required
  Desired
Provide high-level class name(s) associated with each